## Sheet1
Group 4 - Ahmad, Nicholas, Trinidad
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  | Team Member
|  |  | Week 1 | Week 2
Task Management | Can view tasks on the project board in the different stages | 0.5 | 0.5 | 0.5
| Implement and test creating/deleting a task on the board (manager, admin, project lead) | 2 | 2 | 2 | Ahmad
| Implement and test updating stage of assigned Task (autodrop assignment, proper assignment if stage is assigned to group) | 2 | 2 | 2
| Implement assigning a Task on the board to myself | 1 | 1 | 1
| Implement assign a Task on the board to a member of my group (manager) | 1 | 1 | 1
| Implement view to Add task | 1 | 1 | 1 | Ahmad
| Implement view to edit/delete task (editing should be based on user perms) | 1 | 1 | 1
| Implement Database for task management | 1 | 1 | 1 | Ahmad
Task Management Models | Implement and test Model classes for task management | 3 | 3 | 2 | Nick
Sprint 2 Issues | group page should list manager with group names | 1 | 1 | 0 | Ahmad
| review tables to ensure ordering of fields (e.g., name of group before name of manager) | 1 | 1 | 1 | Ahmad
| <minor> error message when unable to request group to join indicates when it is due to an existing pending/denied request, but does not clarify that denied requests should be removed before requesting again | 0.5 | 0.5 | 0.5 | Ahmad
| revise project creation to generate default set of stages to the project board (TODO, InProgress, Done) | 1 | 1 | 0 | Nick
| alter edit stage to display stages in the same way as other board views | 1 | 1 | 1 | Nick
Documentation | ER Diagram | 1 | 0 | 0 | Ahmad
| Class Diagram | 1 | 1 | 0 | Trinidad
| Use Case Scenarios | 1 | 0 | 0 | Nick
| Use Case Diagram | 1 | 0 | 0 | Nick
| Estimate Totals | 21 | 18 | 14
Ahmad
Trinidad
Nick
Nick
Ahmad