## Sheet1
Group 4 - Ahmad, Nicholas, Trinidad
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  | Team Member
|  |  | Week 1 | Week 2
Manager - View and Edit a board for a project | Implement base project board page | 4 | 3 | 0 | Nick
| Implement functionality/testing to add stages | 2 | 1 | 0 | Nick
| Implement view to add stages | 2 | 1 | 0 | Nick
| Implement functionality/testing to delete stages | 2 | 1 | 0 | Nick
| Implement view to delete stages | 2 | 1 | 0 | Nick
| Implement functionality/testing to edit stages | 2 | 1 | 0 | Nick
| Implement view to edit stages | 2 | 1 | 0 | Nick
Admin - View and Edit a board for a project | Implement base project board page | 4 | 3 | 0 | Nick
| Implement functionality/testing to add stages | 2 | 1 | 0 | Nick
| Implement view to add stages | 2 | 1 | 0 | Nick
| Implement functionality/testing to delete stages | 2 | 1 | 0 | Nick
| Implement view to delete stages | 2 | 1 | 0 | Nick
| Implement functionality/testing to edit stages | 2 | 1 | 0 | Nick
| Implement view to edit stages | 2 | 1 | 0 | Nick
Employee - View board | Implement base project board page | 1 | 1 | 0 | Nick
Users - Can change password if I forgot it | Implement functionality/testing to change password | 2 | 2 | 0 | Ahmad
| Implement view to forgot password page | 2 | 2 | 0 | Ahmad
Ahmad
Users - I can retrieve my username by email if I forgot username | Implement functionality/testing to send username using the email associated with it | 2 | 2 |  | Ahmad
| Implement view to find username page | 1 | 1 | 0 | Ahmad
Demo notes | (minor) error message centered on login, but not centered on other pages | 2 | 0 | 0 | Trinidad
| manager should be able to add/remove employee from their own group | 2 | 0 | 0 | Trinidad
| user should not be set to a system wide manager role (manager role is based on relationship to group/project) | 1 | 0 | 0 | Trinidad
| should not allow deleting a user that is set as manager for group or group referenced by a project, and should generate appropriate error message prompt to user | 2 | 0 | 0 | Trinidad
| (minor) remove privacy page from site | 0.5 | 0.5 | 0 | Nick
| (minor) update home page to be blank page with the same nav bar as the other pages | 0.5 | 0.5 | 0 | Nick
| ensure forms indicate required fields and other expectations | 2 | 0 | 0 | Trinidad
| most error messages are consistent with a few exceptions. Work to ensure all error messages are consistent | 2 | 0 | 0 | Trinidad
| add filtering/paging/scrolling to support working with large lists | 2 | 0 | 0 | Trinidad
| should set groups in project when creating the project |  |  |  | Ahmad
| add confirmation check when deleting group | 0.5 | 0.5 | 0 | Trinidad
| (minor) display manager for group and lead for project on main page lists |  |  |  | Ahmad
| employee should be able to view all group/project | 2 | 0 | 0 | Trinidad
| manager should be able to edit/delete their own group/project | 2 | 0 | 0 | Trinidad
| system should display groups that have been requested to assign for a project, but have not approved yet |  |  | 0 | Ahmad
Documentation | ER Diagram | 1 | 1 | 0 | Ahmad
| Class Diagram | 1 | 1 | 0 | Trindiad
| Use Case Scenarios | 1 | 1 | 0 | Nick
| Use Case Diagram | 1 | 1 | 0 | Nick
| Sprint Backlog | 1 | 1 | 0 | Nick
| Estimate Totals | 63.5 | 32.5 | 0
Ahmad
Trinidad
Nick
Nick
Ahmad