## Sheet1
Group 4 - Ahmad, Nicholas, Trinidad
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  | Team Member
|  |  | Week 1 | Week 2
Desktop Task | Implement and create view for displaying assigned tasks and available tasks | 1 | 1 | 0 | Ahmad
| Implement and create view for displaying selected task details (name, desc, project name, stage name, assigned to) | 1 | 1 | 0 | Ahmad
| Implement functionality to update stage for a task | 0.5 | 1 | 0 | Ahmad
| Implement functionality to self-assign/unassign to/from a task | 0.5 | 1 | 0 | Ahmad
Task History | Implement and create view for displaying task history | 3 | 3
<optional> Task Comments | Implement and create view for posting comments on tasks (Web) | 2 | 2
| Implement and create view for posting comments on tasks (Desktop) | 2 | 2
Sprint 3 Issues | Change task assignment restrictions | 0.5 | 0 | 0 | Ahmad
| Prevent deleting stage with active tasks | 0.5 | 0 | 0 | Ahmad
| Relabel Edit Task to View Task | 0.05 | 0 | 0 | Ahmad
| Group Assignment should only affect task assignment | 0.5 | 0 | 0 | Ahmad
Documentation | ER Diagram | 1 | 0 | 0 | Ahmad
| Class Diagram | 1 | 1 | 0 | Trinidad
| Use Case Scenarios | 1 | 1 | 0 | Nick
| Use Case Diagram | 1 | 1 | 0 | Nick
| Estimate Totals | 15.55 | 14 | 0
Ahmad
Trinidad
Nick
Nick
Ahmad