## Sheet1
Group 4 - Ahmad, Nicholas, Trinidad
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  |  |  | Team Member
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Implement Database needed for Login | 2 | 0
| Implement Login page (Username / password) | 1 | 0
| Implement Functionality for Login | 2 | 0
Admin - Employee Management | Implement Database needed for Employee Management | 2 | 0
| Implement Page to view Employees | 2 | 0
| Implement Functionality to view Employees | 2 | 0
| Implement Page to create Employees | 2 | 2
| Implement Functionality to create Employees | 2 | 2
| Implement Page to delete Employees | 1 | 0
| Implement functionality to delete Employees | 2 | 0
Admin - Group Management | Implement Database needed for Group Management | 2 | 0 |  |  |  | Trinidad
| Implement Page to view Groups | 2 | 0 |  |  |  | Trinidad
| Implement Functionality to view Groups | 2 | 0 |  |  |  | Trinidad
| Implement Page to Create Groups | 2 | 0 |  |  |  | Trinidad
| Implement Functionality to Create Groups | 2 | 0 |  |  |  | Trinidad
| Implement Page to Delete Groups | 1 | 0 |  |  |  | Trinidad
| Implement functionality to Delete Groups | 2 | 0 |  |  |  | Trinidad
| Implement Page to Assign Employees to Groups | 2 | 0 |  |  |  | Trinidad
| Implement Functionality to Assign Employees to Groups | 2 | 0 |  |  |  | Trinidad
| Implement Functionality to Promote Manager to Group | 1 | 0 |  |  |  | Trinidad
Admin - Project Management | Implement Database needed for Project Management | 2 | 0 |  |  |  | Nick
| Implement Page to view Projects | 2 | 0 |  |  |  | Nick
| Implement Functionality to view Projects | 2 | 0 |  |  |  | Nick
| Implement Page to Create Projects | 2 | 0 |  |  |  | Nick
| Implement Functionality to Create Projects | 2 | 0 |  |  |  | Nick
| Implement Page to Delete Projects | 1 | 0 |  |  |  | Nick
| Implement Functionality to Delete Projects | 2 | 0 |  |  |  | Nick
| Implement Page to edit Project Title & Desc | 2 | 0 |  |  |  | Nick
| Implement Functionality to Edit Project Title & Desc | 1 | 0 |  |  |  | Nick
| Implement Page to Assign/Remove Groups from Project | 2 | 0 |  |  |  | Nick
| Implement Functionality to Assign/Remove Groups from Project | 2 | 0 |  |  |  | Nick
Manager - Project Management | Implement Functionality to Assign/Remove Groups from Project with permission | 2 | 2 |  |  |  | Ahmad
Documentation | ER Diagram | 3 | 0 |  |  |  | Ahmad
| Class Diagram | 2 | 0 |  |  |  | Trinidad
| Use Case Scenarios | 2 | 0 |  |  |  | Nick
| Use Case Diagram | 2 | 0 |  |  |  | Nick
Revise after first sprint meeting
| Estimate Totals | 67 | 6 | 0 | 0 | 0