## Sheet1
Group 4 - Ahmad, Nicholas, Trinidad
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  |  |  | Team Member
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Implement Database needed for Login | 2
| Implement Login page (Username / password) | 1
| Implement Functionality for Login | 2
Admin - Employee Management | Implement Database needed for Employee Management | 2
| Implement Page to view Employees | 2
| Implement Functionality to view Employees | 2
| Implement Page to create Employees | 2
| Implement Functionality to create Employees | 2
| Implement Page to delete Employees | 1
| Implement functionality to delete Employees | 2
Admin - Group Management | Implement Database needed for Group Management | 2
| Implement Page to view Groups | 2
| Implement Functionality to view Groups | 2
| Implement Page to Create Groups | 2
| Implement Functionality to Create Groups | 2
| Implement Page to Delete Groups | 1
| Implement functionality to Delete Groups | 2
| Implement Page to Assign Employees to Groups | 2
| Implement Functionality to Assign Employees to Groups | 2
| Implement Functionality to Promote Manager to Group | 1
Manager - Project Management | Implement Database needed for Project Management | 2
| Implement Page to view Projects | 2
| Implement Functionality to view Projects | 2
| Implement Page to Create Projects | 2
| Implement Functionality to Create Projects | 2
| Implement Page to Delete Projects | 1
| Implement Functionality to Delete Projects | 2
| Implement Page to edit Project Title & Desc | 2
| Implement Functionality to Edit Project Title & Desc | 1
| Implement Page to Assign/Remove Groups from Project | 2
| Implement Functionality to Assign/Remove Groups from Project | 2
Manager - Project Board | Implement Database need for Tasks | 2
| Implement Page to view Tasks on a Kanban board for Project | 4
| Implement Functionality to view Tasks for a Project | 3
| Implement Page to add Tasks to Project | 2
| Implement Functionality to add Tasks for a Project | 2
| Implement Functionality to Delete Tasks for a Project | 1
| Implement Functionality to assign employees from my Group to assigned Task | 3
Revise after first sprint meeting
| Estimate Totals | 73 | 0 | 0 | 0 | 0